## Estimate
Project Name: |  | Hotel Management System
Module Name: |  | Sprint 1
Development Team: |  | Group 8
Start Date: |  | 2025-06-24
End Date: |  | 2025-07-02
On Time
No. | Member Name |  | Estimate |  |  |  | Lately
1 | Lanh | Đỗ Lanh | 38 |  |  |  | Early
2 | Quyen | Trương Thị Mỹ Quyên | 28 |  |  |  | Unfinished
3 | Hoang | Lê Huy Hoàng | 24
4 | Quoc | Phạm Tấn Quốc | 24
5 | Hung | Dương Văn Hùng | 25
Total |  |  | 139
SPRINT 1 REPORT | Conponent | Task Name | Resposible Member | Estimate | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-27 | 2025-06-28 | 2025-06-29 | 2025-06-30 | 2025-07-01 | 2025-07-02
| Sprint Plan Meeting |  | All member | 5 | 0
| Create Sprint Backlog for Sprint 1 |  | Lanh | 4 | 0
| Create Test Plan document for Sprint 1 |  | Lanh | 4 | 4 | 0
Design UI
| Design UI Admin Login/Logout |  | Lanh | 5 | 5 | 5 | 0
| Design UI Hotel Staff Login/Logout |  | Quyen | 5 | 5 | 5 | 0
| Design Room Check-in/Check-out |  | Hoang | 5 | 5 | 5 | 5 | 0
| Design Room Status Update |  | Quoc | 5 | 5 | 5 | 5 | 0
| Design Invoice Generation |  | Hung | 5 | 5 | 5 | 5 | 5 | 0
Database
| Design database |  | Lanh | 4 | 4 | 4 | 4 | 4 | 0
Coding
| (Front-end) Code Admin Login/Logout |  | Lanh | 3 | 3 | 3 | 3 | 3 | 3 | 0
| (Back-end) Code Admin Login/Logout |  | Lanh | 7 | 7 | 7 | 7 | 7 | 7 | 0
| (Front-end) Code Hotel Staff Login/Logout |  | Quyen | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| (Back-end) Code Hotel Staff Login/Logout |  | Quyen | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 0
| (Front-end) Code Room Check-in/Check-out |  | Hoang | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| (Back-end) Code Room Check-in/Check-out |  | Hoang | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
| (Front-end) Code Room Status Update |  | Quoc | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| (Back-end) Code Room Status Update |  | Quoc | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
| (Front-end) Code Invoice Generation |  | Hung | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| (Back-end) Code Invoice Generation |  | Hung | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
Testing and fix bug
| Test Admin Login/Logout |  | Lanh | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Test Hotel Staff Login/Logout |  | Quyen | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Test Room Check-in/Check-out |  | Hoang | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Test Room Status Update |  | Quoc | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Test Invoice Generation |  | Hung | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
Fix Bug & Release Sprint 1
| Implement test case |  | All member | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
| Fix bugs and report |  | All member | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 0
| Retest |  | All member | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0
| Closing |  | All member | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  |  | TOTAL | 139 | 130 | 126 | 116 | 106 | 97 | 87 | 67 | 50 | 0

## Actual
Project Name: |  | Hotel Management System
Module Name: |  | Sprint 1
Development Team: |  | Group 8
Start Date: |  | 2025-06-24
End Date: |  | 2025-07-02
On Time
No. | Member Name |  | Estimate | Actual |  |  | Lately
1 | Lanh | Đỗ Lanh | 38 | 38 |  |  | Early
2 | Quyen | Trương Thị Mỹ Quyên | 28 | 28 |  |  | Unfinished
3 | Hoang | Lê Huy Hoàng | 24 | 24
4 | Quoc | Phạm Tấn Quốc | 24 | 24
5 | Hung | Dương Văn Hùng | 25 | 25
Total |  |  | 139 | 139
SPRINT 1 REPORT | Conponent | Task Name | Resposible Member | Actual | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-27 | 2025-06-28 | 2025-06-29 | 2025-06-30 | 2025-07-01 | 2025-07-02
| Sprint Plan Meeting |  | All member | 5 | 0
| Create Sprint Backlog for Sprint 1 |  | Lanh | 4 | 0
| Create Test Plan document for Sprint 1 |  | Lanh | 4 | 4 | 0
Design UI
| Design UI Admin Login/Logout |  | Lanh | 5 | 5 | 5 | 0
| Design UI Hotel Staff Login/Logout |  | Quyen | 5 | 5 | 0
| Design UI Room Check-in/Check-out |  | Hoang | 5 | 5 | 5 | 5 | 0
| Design Room Status Update |  | Quoc | 5 | 5 | 5 | 0
| Design Invoice Generation |  | Hung | 5 | 5 | 5 | 5 | 5 | 0
Database
| Design database |  | Lanh | 4 | 4 | 4 | 4 | 4 | 0
Coding
| (Front-end) Code Admin Login/Logout |  | Lanh | 3 | 3 | 3 | 3 | 3 | 0
| (Back-end) Code Admin Login/Logout |  | Lanh | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0
| (Front-end) Code Hotel Staff Login/Logout |  | Quyen | 3 | 3 | 3 | 3 | 3 | 3 | 0
| (Back-end) Code Hotel Staff Login/Logout |  | Quyen | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 0
| (Front-end) Code Room Check-in/Check-out |  | Hoang | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| (Back-end) Code Room Check-in/Check-out |  | Hoang | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
| (Front-end) Code Room Status Update |  | Quoc | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| (Back-end) Code Room Status Update |  | Quoc | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
| (Front-end) Code Invoice Generation |  | Hung | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| (Back-end) Code Invoice Generation |  | Hung | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
Testing and fix bug
| Test Admin Login/Logout |  | Lanh | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Test Hotel Staff Login/Logout |  | Quyen | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Test Room Check-in/Check-out |  | Hoang | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Test Room Status Update |  | Quoc | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Test Invoice Generation |  | Hung | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
Fix Bug & Release Sprint 1
| Implement test case |  | All member | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
| Fix bugs and report |  | All member | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 0
| Retest |  | All member | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0
| Closing |  | All member | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  |  | TOTAL | 139 | 130 | 121 | 111 | 106 | 94 | 91 | 67 | 48 | 0

## Chart
Burn down chart Sprint 1
Estimate | Actual | Date
130 | 130 | 2025-06-24
126 | 121 | 2025-06-25
116 | 111 | 2025-06-26
106 | 106 | 2025-06-27
97 | 94 | 2025-06-28
87 | 91 | 2025-06-29
67 | 67 | 2025-06-30
50 | 48 | 2025-07-01
0 | 0 | 2025-07-02