## Estimate
Project Name: |  | Hotel Management System
Module Name: |  | Sprint 2
Development Team: |  | Group 8
Start Date: |  | 2025-07-03
End Date: |  | 2025-07-13
On Time
No. | Member Name |  | Estimate |  |  |  | Lately
1 | Lanh | Đỗ Lanh | 41 |  |  |  | Early
2 | Quyen | Trương Thị Mỹ Quyên | 26 |  |  |  | Unfinished
3 | Hoang | Lê Huy Hoàng | 27
4 | Quoc | Phạm Tấn Quốc | 26
5 | Hung | Dương Văn Hùng | 35
Total |  |  | 155
SPRINT 1 REPORT | Conponent | Task Name | Resposible Member | Estimate | 2025-07-03 | 2025-07-04 | 2025-07-05 | 2025-07-06 | 2025-07-07 | 2025-07-08 | 2025-07-09 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-13
| Sprint Plan Meeting |  | All member | 5 | 0
| Create Sprint Backlog for Sprint 2 |  | Hung | 4 | 0
| Create Test Plan document for Sprint 2 |  | Hung | 4 | 4 | 0
Design UI
| Design Payment Processing |  | Lanh | 5 | 5 | 5 | 0
| Design Billing Adjustments |  | Quyen | 5 | 5 | 5 | 0
| Design Payment History & Receipts |  | Hoang | 5 | 5 | 5 | 5 | 0
| Design Service Request Handling |  | Quoc | 5 | 5 | 5 | 5 | 0
| Design Housekeeping Task Tracking |  | Hung | 5 | 5 | 5 | 5 | 5 | 0
Database
| Design database |  | Lanh | 4 | 4 | 4 | 4 | 4 | 0
Coding
| (Front-end)Code Payment Processing |  | Lanh | 6 | 6 | 6 | 6 | 6 | 6 | 0
| (Back-end)Code Payment Processing |  | Lanh | 10 | 10 | 10 | 10 | 10 | 10 | 0
| (Front-end)Code Billing Adjustments |  | Quyen | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Back-end) Code Billing Adjustments |  | Quyen | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
| (Front-end)Code Payment History & Receipts |  | Hoang | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| (Back-end)Code Payment History & Receipts |  | Hoang | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
| (Front-end) Code Service Request Handling |  | Quoc | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| (Back-end) Code Service Request Handling |  | Quoc | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
| (Front-end) Code Housekeeping Task Tracking |  | Hung | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| (Back-end) Code Housekeeping Task Tracking |  | Hung | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
Testing and fix bug
| Test Payment Processing |  | Lanh | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0
| Test Billing Adjustments |  | Quyen | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
| Test Payment History & Receipts |  | Hoang | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
| Test Service Request Handling |  | Quoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
| Test Housekeeping Task Tracking |  | Hung | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
Fix Bug & Release Sprint 2
| Implement test case |  | All member | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
| Fix bugs and report |  | All member | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 0
| Retest |  | All member | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0
| Closing |  | All member | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  |  | TOTAL | 155 | 146 | 142 | 132 | 122 | 113 | 97 | 81 | 65 | 53 | 40 | 0

## Actual
Project Name: |  | Hotel Management System
Module Name: |  | Sprint 2
Development Team: |  | Group 8
Start Date: |  | 2025-07-03
End Date: |  | 2025-07-13
On Time
No. | Member Name |  | Estimate | Actual |  |  | Lately
1 | Lanh | Đỗ Lanh | 41 | 41 |  |  | Early
2 | Quyen | Trương Thị Mỹ Quyên | 26 | 26 |  |  | Unfinished
3 | Hoang | Lê Huy Hoàng | 27 | 27
4 | Quoc | Phạm Tấn Quốc | 26 | 26
5 | Hung | Dương Văn Hùng | 35 | 35
Total |  |  | 155 | 155
SPRINT 1 REPORT | Conponent | Task Name | Resposible Member | Actual | 2025-07-03 | 2025-07-04 | 2025-07-05 | 2025-07-06 | 2025-07-07 | 2025-07-08 | 2025-07-09 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-13
| Sprint Plan Meeting |  | All member | 5 | 0
| Create Sprint Backlog for Sprint 2 |  | Hung | 4 | 0
| Create Test Plan document for Sprint 2 |  | Hung | 4 | 4 | 0
Design UI
| Design Payment Processing |  | Lanh | 5 | 5 | 5 | 0
| Design Billing Adjustments |  | Quyen | 5 | 5 | 5 | 0
| Design Payment History & Receipts |  | Hoang | 5 | 5 | 5 | 5 | 0
| Design Service Request Handling |  | Quoc | 5 | 5 | 5 | 5 | 0
| Design Housekeeping Task Tracking |  | Hung | 5 | 5 | 5 | 5 | 5 | 0
Database
| Design database |  | Lanh | 4 | 4 | 4 | 4 | 4 | 0
Coding
| (Front-end)Code Payment Processing |  | Lanh | 6 | 6 | 6 | 6 | 6 | 0
| (Back-end)Code Payment Processing |  | Lanh | 10 | 10 | 10 | 10 | 10 | 10 | 0
| (Front-end)Code Billing Adjustments |  | Quyen | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| (Back-end) Code Billing Adjustments |  | Quyen | 5 | 5 | 5 | 5 | 5 | 5 | 0
| (Front-end)Code Payment History & Receipts |  | Hoang | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| (Back-end)Code Payment History & Receipts |  | Hoang | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
| (Front-end) Code Service Request Handling |  | Quoc | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| (Back-end) Code Service Request Handling |  | Quoc | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
| (Front-end) Code Housekeeping Task Tracking |  | Hung | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| (Back-end) Code Housekeeping Task Tracking |  | Hung | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
Testing and fix bug
| Test Payment Processing |  | Lanh | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0
| Test Billing Adjustments |  | Quyen | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
| Test Payment History & Receipts |  | Hoang | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
| Test Service Request Handling |  | Quoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
| Test Housekeeping Task Tracking |  | Hung | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
Fix Bug & Release Sprint 2
| Implement test case |  | All member | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
| Fix bugs and report |  | All member | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 0
| Retest |  | All member | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0
| Closing |  | All member | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  |  | TOTAL | 155 | 146 | 142 | 132 | 122 | 107 | 92 | 84 | 65 | 49 | 40 | 0

## Chart
Burn down chart Sprint 2
Estimate | Actual | Date
146 | 146 | 2025-07-03
142 | 142 | 2025-07-04
132 | 132 | 2025-07-05
122 | 122 | 2025-07-06
113 | 107 | 2025-07-07
97 | 92 | 2025-07-08
81 | 84 | 2025-07-09
65 | 65 | 2025-07-10
53 | 49 | 2025-07-11
40 | 40 | 2025-07-12
0 | 0 | 2025-07-13