## Estimate
Project Name: |  | Hotel Management System
Module Name: |  | Sprint 3
Development Team: |  | Group 8
Start Date: |  | 2025-07-14
End Date: |  | 2025-07-18
On Time
No. | Member Name |  | Estimate |  |  |  | Lately
1 | Lanh | Đỗ Lanh | 30 |  |  |  | Early
2 | Quyen | Trương Thị Mỹ Quyên | 26 |  |  |  | Unfinished
3 | Hoang | Lê Huy Hoàng | 21
4 | Quoc | Phạm Tấn Quốc | 26
5 | Hung | Dương Văn Hùng | 22
Total |  |  | 125
SPRINT 3 REPORT | Conponent | Task Name | Resposible Member | Estimate | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-07-17 | 2025-07-18
| Sprint Plan Meeting |  | All member | 5 | 0
| Create Sprint Backlog for Sprint 3 |  | Hoang | 4 | 0
| Create Test Plan and Database document for Sprint 3 |  | Hoang | 4 | 4 | 0
Design UI
| Design Admin Summarized Operations View |  | Lanh | 4 | 4 | 0
| Design Admin Financial Reports View |  | Quyen | 4 | 4 | 0
| Design Admin Room Price Adjustment Tracking |  | Quoc | 4 | 4 | 0
| Design Admin User Permissions Monitoring |  | Hung | 4 | 4 | 0
Database
| Design database |  | Lanh | 4 | 4 | 4 | 0
Coding
| (Front-end) Code Admin Summarized Operations View |  | Lanh | 3 | 3 | 3 | 3 | 0
| (Back-end) Code Admin Summarized Operations View |  | Lanh | 6 | 6 | 6 | 6 | 0
| (Front-end) Code Admin Financial Reports View |  | Quyen | 4 | 4 | 4 | 4 | 0
| (Back-end) Code Admin Financial Reports Viewt |  | Quyen | 5 | 5 | 5 | 5 | 0
| (Front-end) Code Admin Room Price Adjustment Tracking |  | Hung | 3 | 3 | 3 | 3 | 0
| (Back-end) Code Admin Room Price Adjustment Tracking |  | Hung | 6 | 6 | 6 | 6 | 0
| (Front-end) Code Admin User Permissions Monitoring |  | Quoc | 2 | 2 | 2 | 2 | 0
| (Back-end) Code Admin User Permissions Monitoring |  | Quoc | 7 | 7 | 7 | 7 | 0
Testing and fix bug
| Test Admin Summarized Operations View |  | Lanh | 4 | 4 | 4 | 4 | 4 | 0
| Test Admin Financial Reports View |  | Quyen | 4 | 4 | 4 | 4 | 4 | 0
| Test Admin Room Price Adjustment Tracking |  | Hoang | 4 | 4 | 4 | 4 | 4 | 0
| Test Admin Room Price Adjustment Tracking |  | Quoc | 4 | 4 | 4 | 4 | 4 | 0
| Fix Bug & Release Sprint 3 | [7 empty] | 0
| Implement test case |  | All member | 8 | 8 | 8 | 8 | 8 | 0
| Fix bugs and report |  | All member | 20 | 20 | 20 | 20 | 20 | 0
| Retest |  | All member | 10 | 10 | 10 | 10 | 10 | 0
| Closing |  | All member | 2 | 2 | 2 | 2 | 2 | 0
|  |  | TOTAL | 125 | 116 | 96 | 92 | 56 | 0

## Actual
Project Name: |  | Hotel Management System
Module Name: |  | Sprint 3
Development Team: |  | Group 8
Start Date: |  | 2025-07-14
End Date: |  | 2025-07-18
On Time
No. | Member Name |  | Estimate | Actual |  |  | Lately
1 | Lanh | Đỗ Lanh | 30 | 30 |  |  | Early
2 | Quyen | Trương Thị Mỹ Quyên | 26 | 26 |  |  | Unfinished
3 | Hoang | Lê Huy Hoàng | 21 | 21
4 | Quoc | Phạm Tấn Quốc | 26 | 26
5 | Hung | Dương Văn Hùng | 22 | 22
Total |  |  | 125 | 125
SPRINT 3 REPORT | Conponent | Task Name | Resposible Member | Actual | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-07-17 | 2025-07-18
| Sprint Plan Meeting |  | All member | 5 | 0
| Create Sprint Backlog for Sprint 3 |  | Hoang | 4 | 0
| Create Test Plan and Database document for Sprint 3 |  | Hoang | 4 | 4 | 0
Design UI
| Design Admin Summarized Operations View |  | Lanh | 4 | 4 | 0
| Design Admin Financial Reports View |  | Quyen | 4 | 4 | 0
| Design Admin Room Price Adjustment Tracking |  | Quoc | 4 | 0
| Design Admin User Permissions Monitoring |  | Hung | 4 | 4 | 0
Database
| Design database |  | Lanh | 4 | 4 | 4 | 0
Coding
| (Front-end) Code Admin Summarized Operations View |  | Lanh | 3 | 3 | 3 | 0
| (Back-end) Code Admin Summarized Operations View |  | Lanh | 6 | 6 | 6 | 0
| (Front-end) Code Admin Financial Reports View |  | Quyen | 4 | 4 | 0
| (Back-end) Code Admin Financial Reports Viewt |  | Quyen | 5 | 5 | 5 | 0
| (Front-end) Code Admin Room Price Adjustment Tracking |  | Hung | 3 | 3 | 3 | 3 | 0
| (Back-end) Code Admin Room Price Adjustment Tracking |  | Hung | 6 | 6 | 6 | 0
| (Front-end) Code Admin User Permissions Monitoring |  | Quoc | 2 | 2 | 2 | 2 | 0
| (Back-end) Code Admin User Permissions Monitoring |  | Quoc | 7 | 7 | 7 | 7 | 0
Testing and fix bug
| Test Admin Summarized Operations View |  | Lanh | 4 | 4 | 4 | 4 | 4 | 0
| Test Admin Financial Reports View |  | Quyen | 4 | 4 | 4 | 4 | 4 | 0
| Test Admin Room Price Adjustment Tracking |  | Hoang | 4 | 4 | 4 | 4 | 4 | 0
| Test Admin Room Price Adjustment Tracking |  | Quoc | 4 | 4 | 4 | 4 | 4 | 0
| Fix Bug & Release Sprint 3 | [7 empty] | 0
| Implement test case |  | All member | 8 | 8 | 8 | 8 | 8 | 0
| Fix bugs and report |  | All member | 20 | 20 | 20 | 20 | 20 | 0
| Retest |  | All member | 10 | 10 | 10 | 10 | 10 | 0
| Closing |  | All member | 2 | 2 | 2 | 2 | 2 | 0
|  |  | TOTAL | 125 | 112 | 92 | 68 | 56 | 0

## Chart
Burn down chart Sprint 3
Estimate | Actual | Date
116 | 112 | 2025-07-14
96 | 92 | 2025-07-15
92 | 68 | 2025-07-16
56 | 56 | 2025-07-17
0 | 0 | 2025-07-18